## Slide 1
GLOBAL OPERATING MODEL
TIXR SCOUT | MARCH 2026 |
RACI | OWNERSHIP MATRIX
TASK | ENG | CS | OPS | DATA | SALES
Market selection (SCOUT Opp. Score) | I | I | A | R | C
Venue BD (Ziggo Dome, Swiss Life…) | I | I | C | C | A
Payment integration (iDEAL/SEPA/BPAY) | A | C | R | I | I
Partner onboarding (30-day SLA) | C | A | R | I | C
Follow-the-sun support (SM>LDN>SYD) | C | A | R | I | I
SCOUT pipeline refresh + re-scoring | I | I | I | A | R
A = Accountable (1 per row) | R = Responsible | C = Consulted | I = Informed
CAPABILITY GAPS | TIERED PRIORITIES
LAUNCH BLOCKERS — DAY 1
iDEAL / SEPA / Klarna / BPAY checkout
ENG | 2-week sprint
GDPR + AU Privacy Act compliance
LEGAL | Day 1
Follow-the-sun CS coverage
HIRE | By Day 20
Fraud & chargeback handling
ENG+OPS | Pre-launch
BUILD BY MONTH 3 — BUILD / BUY
SCOUT V2 daily cron refresh
BUILD | ~$5/mo API
NL/DE/EN localization engine
BUILD | Checkout + portal
Partner self-serve onboarding
BUILD | 820 NL long-tail
Germany GmbH + Country Mgr hire
OPS+LEGAL | By Week 6
Hub: Regional Lead Amsterdam (NL+DE) | AU contractor -> VP Intl | 496 T1 targets (297 DE + 83 NL + 116 AU)
OPERATING CADENCE
GOVERNANCE LOOP | HOW SIGNALS DRIVE DECISIONS
WEEKLY
SCOUT T1 pipeline by market | BuyButton hit rate | BD conversion funnel
MONTHLY
Market churn (NL/DE/AU) | Payment failure rate | Opp. Score delta vs. prior month
QUARTERLY
Board OKR: venues signed vs. 90-day target | Market gate go/no-go decision
ANNUAL
Next market decision: Japan #4 (76.0) or Spain #5 (73.9)? Org design reset
FIELD DATA IN
Continuous
SCOUT alerts + daily refresh
BuyButton ground truth
Rep field notes + BD calls
CS support queue signals
Owner: Data + Sales
>
WEEKLY REVIEW
Every Monday
T1 pipeline vs. target
BuyButton hit rate by mkt
BD conversion funnel
Rep-flagged blockers
Owner: VP Intl + BDR Lead
>
MONTHLY GATE
1st of month
Opp. Score trend (+-5pts)
Payment failure rate >3%
CS surge >2x baseline
Venue churn or re-sign risk
Owner: CS + Ops + Data
>
STRATEGY ADJUST
Decision output
Pause / accelerate market
Re-run SCOUT model
Redirect BD headcount
Board escalation if needed
Owner: VP Intl + Board
<
FEEDBACK LOOP | Execution updates re-score SCOUT model and adjusts field priorities
ESCALATION TRIGGERS: BD pipeline miss >20% | Payment failure >3% | CS surge >2x baseline | Venue re-sign at risk (Crown Perth) | Opp. Score drop >5pts -> VP Intl + Board
TIXR SCOUT | 18,311 VENUES | 98 MARKETS | TOP 3: NETHERLANDS (80.8) -> GERMANY (78.5) -> AUSTRALIA (77.2) | 3,404 ACTIONABLE TARGETS (T1+T2)
<